## Sheet1
|  | From Previous Loi Report |  |  | Construction Cost | IN Cr | 4% Construction Cost | 45 Rs/sqft in Appointment Letter
|  | Sqm | Sqft | Loading
| Rehab | 2220 | 23896.08 | 35844.12 | 107532360 | 10.7532 | 0.43013
| Sale | 3099 | 33357.636 | 50036.454 | 175127589 | 17.5128 | 0.70051
|  |  |  | 85880.574 | 282659949 | 28.266 | 1.1306 | 0.38646
According to 4%
Stage | Part Stage | Payment % | Payment value | Part Payment Value | Payment Recieved Date | Payment Amount Recieved
Propsal Submission |  | 0.5% | 0.14133
| 0.50% Out of total fees payable on Submission of scrutiny for Proposal Submission | 0.25% |  | 0.070665
| 0.50% Out of total fees payable on getting Proposal Submitted | 0.25% |  | 0.070665
SRA Stage |  | 2% | 0.56532
| on Acceptance in SRA | 0.25% |  | 0.070665
| on Getting NOC’s III-finance Controller, IV-DSLR, VI –Town Planning. | 0.25% |  | 0.070665
| Submission on scrutiny fees | 0.3% |  | 0.084798
| Annexure III | 0.3% |  | 0.084798
| Getting of LOI | 0.3% |  | 0.084798
| Getting of IOA Rehab | 0.15% |  | 0.042399
| Getting of IOA Sale | 0.15% |  | 0.042399
| Getting on C.C. Rehab | 0.15% |  | 0.042399
| Getting on C.C. Sale | 0.15% |  | 0.042399
Further Stage |  | 1% | 0.28266
| FCC of Rehab Building | 0.5% |  | 0.14133
| FC.C. of Sale Building | 0.5% |  | 0.14133
O.C.C |  | 0.5% | 0.14133
| Occupation of Rehab Building | 0.25% |  | 0.070665
| Occupation of Sale Building | 0.25% |  | 0.070665
Rehab
Sale

## Sheet2
100000