## Sheet1
|  | From Previous Loi Report |  |  | Construction Cost | IN Cr | 4% Construction Cost | 45 Rs/sqft in Appointment Letter
|  | Sqm | Sqft | Loading
| Rehab | 2220 | 23896.08 | 35844.12 | 107532360 | 10.7532 | 0.43013
| Sale including fungible | 4183.65 | 45032.8086 | 67549.2129 | 236422245.15 | 23.6422 | 0.94569
|  |  |  | 103393.3329 | 343954605.15 | 34.3955 | 1.3758 | 0.46527
According to 4%
Stage | Part Stage | Payment % | Payment value | Part Payment Value | Payment Recieved Date | Payment Amount Recieved
Propsal Submission |  | 0.5% | 0.17198
| 0.50% Out of total fees payable on Submission of scrutiny for Proposal Submission | 0.25% |  | 0.085989
| 0.50% Out of total fees payable on getting Proposal Submitted | 0.25% |  | 0.085989
SRA Stage |  | 2% | 0.68791
| on Acceptance in SRA | 0.25% |  | 0.085989
| on Getting NOC’s III-finance Controller, IV-DSLR, VI –Town Planning. | 0.25% |  | 0.085989
| Submission on scrutiny fees | 0.3% |  | 0.10319
| Annexure III | 0.3% |  | 0.10319
| Getting of LOI | 0.3% |  | 0.10319
| Getting of IOA Rehab | 0.15% |  | 0.051593
| Getting of IOA Sale | 0.15% |  | 0.051593
| Getting on C.C. Rehab | 0.15% |  | 0.051593
| Getting on C.C. Sale | 0.15% |  | 0.051593
Further Stage |  | 1% | 0.34395
| FCC of Rehab Building | 0.5% |  | 0.17198
| FC.C. of Sale Building | 0.5% |  | 0.17198
O.C.C |  | 0.5% | 0.17198
| Occupation of Rehab Building | 0.25% |  | 0.085989
| Occupation of Sale Building | 0.25% |  | 0.085989
Rehab
Sale

## Sheet2
100000